## Plan
Initial Work
1. Collect Requirements
2. Collect Existing Project
3. Stripe the Application and find out functional dependencies
4. Decide on improvements
Development
1. Build new UI plan
2. Debug and make app work
3. Build working form validation
4. Build two factor authentication
5. Build Database Encryption and Decryption Function
6. Build bulk import function to import questions
7. Implement UI Plan
8. Integrated Testing on each function build
Final
1. Load Questions
2. Test everything
3. Tweak the application for improvements

## WBS (Inherited&Updated)
Work Breakdown Structure
PROJECT SYSTEM | [8 empty] | OTHER PROJECT TOOLS
Level 1 WBS | [5 empty] | 0. ASQ CSQE Web App |  |  | Project Name
Level 2 WBS | 1. Front-End |  |  |  |  | 2. Back-End | 3. Database |  | Phase/ Component
Level 3 WBS | 1.1 User Log-in/logout | 1.2 Create User Account | 1.3 Practice Mode" | 1.4 Exam Mode Mode" | 1.5 Front View Template Mode" | 2.1 Log In/Log Out Validation | 3.1 Create Db | 3.2 Upload Questions | Task
| 1.1.1 Req'd fields Validation | 1.2.1 Format Validation (email + fields req) | 1.3.1 ModeSelection | 1.4.1 Mode Selection | 1.5.1 Add Additional Pages | 2.2 Create Account | 3.1.1 Db schema | 3.2.1 Save Results
|  | 1.2.2 Password Validation | 1.3.2 Display Questions | 1.4.2 Display Questions |  | 2.3 Query Db and send results to frontend | 3.1.2 Data Encrypt | 3.2.2 Bulk Import Questions
|  | 1.2.3 Two Factor Authentication | 1.3.3 Grade Questions & Display Results | 1.4.3 Grade Questions & Display Results |  |  | 3.1.3 Data Decrypt
1.4.4 Countdown Timer

## Work Estimation
Task | Assigned To | Work Load (in days) | Status | Comments
Collect Requirements
Collect Existing Project
Stripe Application and Find Dependencies
Decide on Improvements
Debug and Make Application Work
Test Application to build Initial Test Cases
Build New UI plan
Build Updated Form Validations
Integrate Form Validations
Test New Integration
Update Test Cases
Build DB Encrypt/Decrypt Function
Trial Integrate DB Encrypt/Decrypt Function
Test Integreation
Update Test Cases
Build Two Factor Authentication Function
Integrate TFA Function
Test Integreation
Update Test Cases
Build Bulk Import Function
Integrate Bulk Import Function
Test Integreation
Update Test Cases
Build Phase 1 UI Design
Integrate Phase 1 UI Design
Test Integreation
Update Test Cases
Build Phase 2 UI Design
Integrate Phase 2 UI Design
Test Integreation
Update Test Cases
Build Final UI Design
Integrate Final Design
Test Integreation
Update Test Cases
Build Question Bank
Import Question Bank
Test Quiz Modules
Update Test Cases
Populate Other Pages
Test Contact Page enquiry form
Build Final Test Cases
Fix Final Issues
Test Integration
Final Tweak to Application
Perfrom Full Test
Deliver Application

## Budget
Project Budget |  | Project is expect to be delivered in 12 weeks time
Item Description |  | Weekly Cost | Duration | Total Cost
Development |  | 5000 | 12 | 60000
Infrastructure |  | 2500 | 12 | 30000
Buffer & Overhead |  | 1000 | 12 | 12000
Startup Discount |  | - | - | -2000
|  |  | Total | 100000
Development Cost
Team Member | No.s | Weekly Cost | Total Cost
Project Manager | 1 | 1000 | 1000
System Architect | 1 | 900 | 900
Developers | 2 | 850 | 1700
QA Team | 2 | 700 | 1400
|  | Total | 5000